Instructions for Preparing Schedule of Values and Application for Payment

Schedule of Values Tab

SUBCONTRACTOR NAME		Your Company’s Full Name

ADDRESS				Your Company’s Full Address –  where checks

should be sent

PAYMENT APP #			The sequential numbering of your Pay Applications

APPLICATION DATE			The date you’re sending the Pay App to us

PERIOD THROUGH			The  last day of the month for which you are billing

PROJECT NAME			The name of the job on which you are working

SUBCONTRACT #			The number JMW has assigned to your Contract,

found on the 2nd line of your Contract.

Col B – Description of Work		These items are found in your Scope of Work

Col C – Scheduled Value		These amounts are found in your Scope of Work

FOR PAY APP #1

Col E – This Period			Fill in value of work to be completed for the month

for each line item

Columns G, H & I will automatically fill.

FOR SUBSEQUENT PAY APPS

Col D – update figures from		On each line, add the figures in Col D & E and record 		 last month			them in Col D

Col E – record work performed		Fill in amount for work completed for the month

Col F – record stored materials		Fill in amount for stored materials

Col I – Verify Retainage %		To change or release retainage %, change amount

in cell “I-16”

Go to the Application for Payment Tab

SALES & USE TAX #:			Enter your State issued Sales & Use Tax number.

Amount of Sales & Use Tax:		Enter the amount of Sales & Use Tax you paid

for materials on this Pay Application.

PERIOD WORK COMPLETED  From	The first day of the month for which you 							are billing (Ex. 8/01/10)

PERIOD WORK COMPLETED To	The end of the month for which you are billing

(Ex. 08/31/10)

Original Contract Amount		The original amount of your contract

Approved Change Orders		Fill in Approved C.O. #s

The total of Approved Change Orders

Revised Contract Amount		The total of the Original Contract plus or minus the 						Approved Change Orders.  This is also the total of 						Column C on your Schedule of Values.

1. Value of Work Complete to Date	Already filled in

2. Material Stored on Site		Already filled in

3. Total Complete and Stored to Date	Already filled in

4. Less Retainage			Already filled in

5. Total Less Retainage			Already filled in

6. Total Previously Certified		Fill in Line 5 from previous Pay Application

7. Net Due This request			Already filled in

Company Name				Already filled in

Authorized Signature			Signature of individual authorized to sign Pay Application

Title					Officer’s Title

Date					The day the Pay Application is executed

Notary Public				Pay Application must be Notarized

Go to the Statement of Subcontractor Tab

Fill in highlighted areas			Record the job owner’s name, the type of work

you’re performing and the job address.

1. Sub-Subcontractors/Suppliers Name	List names of any Sub-Subcontractors/Suppliers used

on this project.

2. Their Subcontract or PO Amount	The committed amount this sub/supplier is expected

to be paid

3. Value of Work Completed		The amount completed to date

4. Amount Previously Paid		The amount you have paid this sub/supplier on this job

5. Amount Currently Due		The amount due your sub/supplier on this job

(Col 3 – Col 4)

Fill in dates and signatures of authorized individual.

Document must be notarized.